## 100-Day Integration Plan
Harbor Consulting — 100-Day Post-Acquisition Integration Plan
Fill in Owner, dates, and Status for each task. Add or delete rows as needed. Yellow cells are yours to edit; Priority and Status use dropdowns.
Progress: | Total | Complete | In Progress | Not Started | Blocked
| 20 | 0 | 0 | 20 | 0
Phase | Workstream | Task | Owner | Priority | Start (Day) | Due (Day) | Status | Notes
Day 1 | Communications | Deliver Day-1 announcement to employees, customers, and partners |  | Medium | 1 | 1 | Not Started
Day 1 | People / HR | Confirm org structure, reporting lines, and key-person retention |  | Medium | 1 | 1 | Not Started
Day 1 | Finance & Accounting | Secure banking access, signatories, and cash controls |  | Medium | 1 | 1 | Not Started
Day 1 | Systems / ERP | Inventory current systems and confirm access & security |  | Medium | 1 | 1 | Not Started
Day 1 | Legal & Compliance | Confirm insurance, licenses, and required registrations |  | Medium | 1 | 1 | Not Started
First 30 Days | Finance & Accounting | Establish combined chart of accounts and close calendar |  | Medium | 1 | 30 | Not Started
First 30 Days | Finance & Accounting | Stand up consolidated reporting package |  | Medium | 1 | 30 | Not Started
First 30 Days | Finance & Accounting | Integrate AP / AR processes and approvals |  | Medium | 1 | 30 | Not Started
First 30 Days | Systems / ERP | Decide target ERP / finance system and integration approach |  | Medium | 1 | 30 | Not Started
First 30 Days | People / HR | Integrate payroll and benefits; finalize retention plans |  | Medium | 1 | 30 | Not Started
First 30 Days | Reporting & KPIs | Define combined KPIs and management dashboard |  | Medium | 1 | 30 | Not Started
First 30 Days | Commercial / Customers | Customer communications and account transition plan |  | Medium | 1 | 30 | Not Started
First 30 Days | Operations | Map key processes and identify quick wins |  | Medium | 1 | 30 | Not Started
Days 31-100 | Systems / ERP | Execute data migration and system integrations |  | Medium | 31 | 100 | Not Started
Days 31-100 | Finance & Accounting | Refresh combined budget and forecast |  | Medium | 31 | 100 | Not Started
Days 31-100 | Reporting & KPIs | Deliver first full board / investor reporting package |  | Medium | 31 | 100 | Not Started
Days 31-100 | Operations | Rationalize vendors and review key contracts |  | Medium | 31 | 100 | Not Started
Days 31-100 | Commercial / Customers | Review pricing, contracts, and cross-sell opportunities |  | Medium | 31 | 100 | Not Started
Days 31-100 | People / HR | Align roles, compensation, and performance framework |  | Medium | 31 | 100 | Not Started
Days 31-100 | Communications | Run 100-day check-in and capture lessons learned |  | Medium | 31 | 100 | Not Started